## Hardware_OnPrem
Task ID | Action Item | Description | Example/Artifact | Status | Owner | Completion Date
HW-01 | Inventory Verification | Cross-reference physical asset with CMDB. | CMDB entry matched | Pending
HW-02 | Network Disconnection | Isolate device from production LAN/VLAN. | Port disabled on switch | Pending
HW-03 | Data Sanitization | Cryptographic wipe or overwrite per NIST 800-88. | Certificate of Destruction (CoD) | Pending
HW-04 | Asset Tag Removal | Remove enterprise tracking and asset tags. | Photograph of clean chassis | Pending
HW-05 | Physical Rack Removal | Unmount from server rack and disconnect power. | Rack U-space marked available | Pending
HW-06 | Secure Transit | Log chain of custody to disposal facility. | Shipping manifest signed | Pending
HW-07 | Lease/Disposal Closure | Return to lessor or e-waste recycling. | Final e-waste receipt | Pending

## Cloud_Resources
Task ID | Action Item | Description | Example/Artifact | Status | Owner | Completion Date
CL-01 | Dependency Mapping | Ensure no active services depend on the resource. | CloudTrail/Log analytics review | Pending
CL-02 | Final Snapshot | Take final backup of volume/database. | AMI or RDS Snapshot ID logged | Pending
CL-03 | Compute Termination | Terminate EC2/VM instances. | Instance state: Terminated | Pending
CL-04 | Storage Deletion | Empty and delete S3/Blob storage buckets. | Bucket deletion confirmation | Pending
CL-05 | Network Cleanup | Release Elastic IPs, delete subnets/VPCs. | EIP released to pool | Pending
CL-06 | IAM Revocation | Delete specific IAM roles and policies. | IAM Policy deletion log | Pending
CL-07 | Billing Verification | Confirm resource is removed from billing alerts. | Cost Explorer zeroed out | Pending

## Software_Licenses
Task ID | Action Item | Description | Example/Artifact | Status | Owner | Completion Date
SW-01 | Seat Reclamation | Remove user assignment from license portal. | SaaS dashboard shows +1 free seat | Pending
SW-02 | Local Uninstallation | Run remote uninstall script on endpoint. | SCCM/Intune success log | Pending
SW-03 | KMS Key Revocation | Revoke associated decryption/license keys. | KMS revocation event | Pending
SW-04 | Subscription Cancel | Cancel auto-renewal for standalone software. | Vendor email confirmation | Pending
SW-05 | Vendor Notification | Notify vendor of reduced enterprise footprint. | Contract addendum | Pending
SW-06 | Compliance Update | Update internal software audit records. | Audit ledger entry | Pending
SW-07 | Cost Center Adjustment | Remove line item from departmental budget. | Finance portal updated | Pending

## Applications_Data
Task ID | Action Item | Description | Example/Artifact | Status | Owner | Completion Date
APP-01 | DNS Deletion | Remove A, CNAME, and TXT records. | Route53/DNS zone updated | Pending
APP-02 | SSL Revocation | Revoke TLS/SSL certificates for the app. | Certificate Authority CRL updated | Pending
APP-03 | Service Account Disable | Disable app-to-app service accounts. | AD/IAM service account locked | Pending
APP-04 | Data Archival | Export relational/NoSQL data to cold storage. | Glacier/Cold blob archive created | Pending
APP-05 | API Gateway Removal | Deprecate and delete API endpoints. | Swagger/OpenAPI spec retired | Pending
APP-06 | Secrets Deletion | Purge database credentials from Secrets Manager. | HashiCorp Vault/AWS Secrets empty | Pending
APP-07 | App Service Teardown | Delete Kubernetes namespaces or App Services. | kubectl delete ns executed | Pending

## Personnel_Access
Task ID | Action Item | Description | Example/Artifact | Status | Owner | Completion Date
ID-01 | IdP Suspension | Disable Active Directory or SSO (Okta) account. | AD userObject status = Disabled | Pending
ID-02 | MFA Revocation | Revoke Duo/Authenticator tokens. | MFA device wiped from portal | Pending
ID-03 | VPN Termination | Disable VPN client access and profiles. | Cisco/PaloAlto VPN log | Pending
ID-04 | SSH/GPG Key Invalidation | Remove public keys from authorized_keys/Git. | GitHub/GitLab keys revoked | Pending
ID-05 | Mailing List Removal | Remove user from distribution lists. | Exchange/Workspace group updated | Pending
ID-06 | Physical Badge Access | Deactivate RFID/building access badge. | Lenel/Kantech system disabled | Pending
ID-07 | Device Recovery | Retrieve laptop, phone, and peripherals. | IT Helpdesk hardware receipt | Pending